## Sheet1
Sprint 1 Backlog (Sat., Sep. 24 - Fri., Oct. 7)
[6 empty] | 2016-09-24 |  | 2016-09-25 |  | 2016-09-26 |  | 2016-09-27 |  | 2016-09-28 |  | 2016-09-29 |  | 2016-09-30 |  | 2016-10-01 |  | 2016-10-02 |  | 2016-10-03 |  | 2016-10-04 |  | 2016-10-05 |  | 2016-10-06 |  | 2016-10-07
ID Number | Name | Story | Definition of Done | Initial Estimated Hours to Completion | Team Member Responsible for Backlog Item | End of Day 1 - Hours Spent Working | End of Day 1 - Estimated Hours Remaining | End of Day 2 - Hours Spent Working | End of Day 2 - Estimated Hours Remaining | End of Day 3 - Hours Spent Working | End of Day 3 - Estimated Hours Remaining | End of Day 4 - Hours Spent Working | End of Day 4 - Estimated Hours Remaining | End of Day 5 - Hours Spent Working | End of Day 6 - Estimated Hours Remaining | End of Day 6 - Hours Spent Working | End of Day 6 - Estimated Hours Remaining2 | End of Day 7 - Hours Spent Working | End of Day 7 - Estimated Hours Remaining | End of Day 8 - Hours Spent Working | End of Day 8 - Estimated Hours Remaining | End of Day 9 - Hours Spent Working | End of Day 9 - Estimated Hours Remaining | End of Day 10 - Hours Spent Working | End of Day 10 - Estimated Hours Remaining | End of Day 11 - Hours Spent Working | End of Day 11 - Estimated Hours Remaining | End of Day 12 - Hours Spent Working | End of Day 12 - Estimated Hours Remaining | End of Day 13 - Hours Spent Working | End of Day 13 - Estimated Hours Remaining | End of Day 14 - Hours Spent Working | End of Day 14 - Estimated Hours Remaining
1 | Develop UI (Pop-Up) | I want to click on the extension icon and see a pop-up menu with the option to block a new URL, block the current URL, see the countdown timer (be it for the current one-time session or the daily session), and add to and check off items from the to-do list. | When the user can click on the extention's button and see a pop-up with all the aforementioned items and tasks. | 4 | Jake | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Develop UI (Menu) | I want to create a "homepage" menu for our extension so that our users can customize the app as they see fit, adding URLs to be blocked, as well as setting times for such sites to be blocked | When there is a button that brings us to the main page of our extension, and we can add sites to be blocked and adjust times for those sites to be blocked | 6 | Striebel | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 2 | 4 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Develop Blocked Sites Sub-Menu | I want to navigate to a sub menu to add to my blacklist. | When the user can navigate to the sub-menu and add a site to the blacklist. It is stored in the list, but there may not yet be the functionality to actually block it. | 5 | Striebel | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 1 | 4 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0
4 | Develop Allowed Sites Sub-Menu | I want to navigate to a sub menu to add to my whitelist. | When the user can navigate to the sub-menu and add a site to the whitelist. It is stored in the list, but the functionality to block all other sites may not be built in yet. | 5 | Striebel | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 1 | 4 | 0 | 4 | 0 | 1 | 1 | 0 | 0 | 0
5 | Develop Study Timer Sub-Menu | I want to navigate to a sub menu to set a one-time timer for blocking sites. | When the user can navigate to the sub-menu and set the timer to the desired time. The timer counts down, but the functionality to block sites for that period of time may not be built in yet. | 5 | Woloschek | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Develop To-Do List Sub-Menu | I want to navigate to a sub menu to add to or edit my to-do list. | When the user can navigate to the sub-menu and and items to their to-do list. The items can be checked-off, but sites may not yet be blocked up until all items are completed. | 5 | Andrew | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 2 | 2 | 0 | 2 | 0 | 2 | 1 | 2 | 0 | 2
7 | Develop Daily Timer Sub-Menu | I want to navigate to a sub menu to set up a daily time period for blocking sites. | When the user can navigate to the sub-menu and specify the time period each day for which they what their blacklist or whitelist to take effect. The timer counts down each day, but it may not yet block the sites for that period of time. | 5 | Mager | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 1 | 4 | 1 | 3 | 1 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Develop Help/Documentation Sub-Menu | I want to navigate to a sub menu to view information and instructions for the extension. | When the user can navigate to the sub-menu and view the basic description/information for the extension. The information may not be complete, as not all features/functionality of the extension are determined yet. | 5 | Andrew | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | URL Storage | I want to set up a list of URL's that are usable by the extension to block sites. | When I can travel to a website and it does not let me browse it. | 6 | Collin and Jake | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 2 | 4 | 1 | 3 | 1 | 2 | 3 | 5 | 0 | 5